## CAI Tickets
ID | Week | Section | Title | Size | Depends | Description / Acceptance | Completion | Blockers
CAI-001 | Week 1 | RAG core | Confirm FarmCore repo + Compose stack boots | M | — | ✅ `docker-compose.yml` + `farmcore/` | Done
CAI-002 | Week 1 | RAG core | Scaffold Django apps (`accounts`, `farms`, `documents`, `assistant`, `scheduling`) | M | CAI-001 | ✅ | Done
CAI-003 | Week 1 | RAG core | Agree `document_chunks` schema on paper | M | CAI-002 | ✅ `shared/schemas/document_chunks.md` + model | Done
CAI-004 | Week 1 | RAG core | Implement `RetrievalScope` dataclass + validation | M | CAI-003 | ✅ `assistant/scope.py` | Done
CAI-005 | Week 1 | RAG core | Declare port interfaces + no-op adapters | M | CAI-003 | ✅ `assistant/ports/` | Done
CAI-006 | Week 1 | RAG core | Scaffold four registries + version constants | S | CAI-005 | ✅ `assistant/registries/` | Done
CAI-007 | Week 1 | RAG core | Define `chunks-v1` schema + standalone validator | M | CAI-003 | ✅ `shared/schemas/chunks-v1.schema.json` | Done
CAI-008 | Week 1 | RAG core | Audit event schema + `VersionTuple` + migration | M | CAI-002 | ✅ `assistant/models.py` + `versions.py` | Done
CAI-009 | Week 1 | RAG core | OpenAPI design freeze with UI team | S | — | ✅ `docs/OPENAPI_FREEZE.md` (UI sign-off pending) | Done (partial) | UI team sign-off on OPENAPI_FREEZE.md pending
CAI-010 | Week 1 | RAG core | Stub `POST /api/assistant/messages` E2E | L | CAI-004, CAI-008, CAI-009 | ✅ `POST /api/assistant/messages` | Done
CAI-011 | Week 1 | RAG core | CI: scope-integrity + cross-farm leak test skeletons | M | CAI-010 | ✅ `tests/farmcore/` (14 tests) | Done
CAI-012 | Week 1 | RAG core | Pin extraction tooling in `requirements.txt` | S | — | ✅ `pymupdf` pinned in `ingest/requirements.txt`. | Done
CAI-013 | Week 1 | RAG core | **Done (pre-sprint)** Tier A PDF text extraction | — | CAI-012 | ✅ 605 extracted, 34 empty, 0 failed → `data/text/source/`, `tier_a_pdf_text.jsonl`. | Done
CAI-014 | Week 1 | RAG core | Tier A manifest filter (`TIER_EXCLUDED`) | S | CAI-013 | ✅ `ingest/scraper/corpus_filter.py` + `filter-corpus` CLI → `rejected.jsonl` (197 non–Tier A). | Done
CAI-015 | Week 1 | RAG core | Pre-chunk filters: empty + untitled | M | CAI-014 | ✅ `EMPTY_EXTRACTION` (<50 tok), `LIKELY_NON_TEXT_ASSET` (untitled + <100 tok). | Done
CAI-016 | Week 1 | RAG core | Near-duplicate detection + pointer | M | CAI-015 | ✅ Similarity ≥0.9 → reject with `kept_doc_id` (4 pairs found). | Done
CAI-017 | Week 1 | RAG core | Boilerplate stripper | M | CAI-015 | ✅ Repeated short lines + nav blocklist → `data/text/clean/`. | Done
CAI-018 | Week 1 | RAG core | Manual review: 34 empty extractions | M | CAI-013 | ✅ All 34 `ocr_recoverable` — `empty_extractions_review.md` + `.jsonl` + OCR probe | Done
CAI-019 | Week 1 | RAG core | Manual review: 30-doc near-dup sample | S | CAI-016 | ✅ 4/4 pairs confirmed — `near_duplicate_review.md` | Done
CAI-020 | Week 1 | RAG core | Extraction quality report | M | CAI-015–017 | ✅ `data/manifests/extraction_quality_report.json` + `.md`. | Done
CAI-021 | Week 1 | RAG core | CI assertion: 605/34 extraction split | S | CAI-013, CAI-020 | ✅ `ingest/tests/test_extraction_baseline.py`. | Done
CAI-022 | Week 2 | RAG core | Structure-aware chunker (headings → paragraphs) | L | CAI-017, CAI-007 | 300–500 tok, ~15% overlap within section; never split table mid-row; never cross heading. | Not started | OCR fallback not yet wired — 34 scans still empty in text/source (OCR probe proved recoverable)
CAI-023 | Week 2 | RAG core | Parent-child chunk hierarchy | M | CAI-022 | Children embedded/matched; parents for generation; every child has resolvable `parent_id`. | Not started
CAI-024 | Week 2 | RAG core | Table chunks with captions | M | CAI-022 | Separate chunks; one-sentence caption prepended; `parent_id` link. | Not started
CAI-025 | Week 2 | RAG core | Chunk metadata completeness | M | CAI-022 | `content_hash`, `heading_path`, `section_path`, `source_url`, `tier` on every chunk. | Not started
CAI-026 | Week 2 | RAG core | Snapshot builder CLI | L | CAI-023–025 | Outputs `manifest.json`, `chunks.jsonl`, `parents.jsonl`, `rejected.jsonl`, `checksums.txt`; `snapshot_id = gov-a-<YYYYMMDD>-<hash12>`. | Not started
CAI-027 | Week 2 | RAG core | Snapshot validation gates | M | CAI-026 | Hard-fail: no chunk >500 tok; non-null `source_url` + `tier`; all `parent_id` resolve. | Not started
CAI-028 | Week 2 | RAG core | Publish first Tier A snapshot | M | CAI-027 | From 605 clean docs; idempotent rebuild → identical `snapshot_id`. | Not started | Depends on OCR re-extract for full ~635-doc corpus (optional)
CAI-029 | Week 2 | RAG core | Sample review: 20 random chunks | S | CAI-028 | Manual read confirms self-contained, correctly attributed chunks. | Not started
CAI-030 | Week 2 | RAG core | Select + pin embedding model | M | CAI-028 | Model chosen; dimension documented; cost/latency estimate for full corpus. | Not started | Embedding model choice not finalized
CAI-031 | Week 2 | RAG core | Migrate `embedding vector(dim)` on `document_chunks` | M | CAI-030, CAI-003 | Migration applied; gov rows `farm_id = NULL`, `index_key = 'gov_tier_a'`. | Not started
CAI-032 | Week 2 | RAG core | Snapshot import management command | L | CAI-028, CAI-031 | Checksum verify, schema validate, transactional insert, embed jobs enqueued, activate only when 100% embedded. | Not started
CAI-033 | Week 2 | RAG core | `corpus_snapshots` table + atomic activation | M | CAI-032 | Exactly one active row; rollback = pointer flip. | Not started
CAI-034 | Week 2 | RAG core | HNSW partial index (gov dense) | M | CAI-031 | Partial index for `index_key = 'gov_tier_a'`; query plan checked. | Not started
CAI-035 | Week 2 | RAG core | Dense retrieval path via `RetrievalScope` | L | CAI-004, CAI-034 | SQL scope predicate; top-k + parent expansion; no post-hoc Python farm filter. | Not started
CAI-036 | Week 2 | RAG core | Wire generation to retrieved context | L | CAI-035, CAI-005 | `POST /api/assistant/messages` returns real answer for gov-only questions (markers optional this week). | Not started
CAI-037 | Week 2 | RAG core | Idempotent re-import test | S | CAI-032 | Same snapshot twice → no duplicate rows, no partial state. | Not started
CAI-038 | Week 2 | RAG core | Cross-farm leak test with gov rows | M | CAI-035 | Tenant query cannot return gov rows mis-scoped; gov query cannot leak farm data. | Not started
CAI-039 | Week 2 | RAG core | Import corrupted snapshot abort test | S | CAI-032 | Bad checksum → active snapshot unchanged. | Not started
CAI-040 | Week 2 | RAG core | Audit: record `snapshot_id` + version tuple | S | CAI-036 | Every assistant response audit row includes pinned snapshot. | Not started
CAI-041 | Week 3 | RAG core | `tsvector` column + GIN partial indexes | M | CAI-035 | Postgres FTS for gov (and tenant partial stub if schema ready). | Not started
CAI-042 | Week 3 | RAG core | Lexical recall path | M | CAI-041 | Tuned for codes, chemical names, dates, machinery IDs. | Not started
CAI-043 | Week 3 | RAG core | RRF fusion (dense-50 + lexical-50) | M | CAI-042 | Weights in `retrieval_config_version`; audit logs stage scores. | Not started
CAI-044 | Week 3 | RAG core | `RerankPort` + cross-encoder integration | L | CAI-043 | Top-50 → top-8; latency measured against §8 budget. | Not started
CAI-045 | Week 3 | RAG core | MMR diversity filter | M | CAI-044 | Suppress near-duplicate chunks in final context. | Not started
CAI-046 | Week 3 | RAG core | Context assembly + token budget | M | CAI-045 | Parent expansion, dedup by `content_hash`, source-class floors. | Not started
CAI-047 | Week 3 | RAG core | Degradation paths (rerank / dense down) | M | CAI-044 | Reranker down → fused order; dense down → lexical-only; flagged in response + audit. | Not started
CAI-048 | Week 3 | RAG core | Capture dense-only baseline metrics | S | CAI-035 | Informal Recall@10 on 20 queries before hybrid merge. | Not started
CAI-049 | Week 3 | RAG core | Prompt registry: citation marker template | M | CAI-036 | Context-only constraint; facts vs general guidance separation. | Not started
CAI-050 | Week 3 | RAG core | Citation resolution + error on orphan markers | M | CAI-049 | Every `[n]` resolves to assembled chunk; unresolvable = hard error. | Not started
CAI-051 | Week 3 | RAG core | `EntailmentPort` + per-claim scoring | L | CAI-050 | Score cited claims; drop/re-cite/downgrade unsupported claims. | Not started
CAI-052 | Week 3 | RAG core | Citation display payload (content-addressed) | M | CAI-050 | UI contract: expanded citation shows exact chunk text model saw. Agree with UI. | Not started | UI contract for expandable citations not signed off
CAI-053 | Week 3 | RAG core | Source-class tags in response | S | CAI-052 | `gov_tier_a` distinguished in payload (tenant classes stubbed). | Not started
CAI-054 | Week 3 | RAG core | Gate signals: confidence, coverage, conflict | L | CAI-046 | Three signals implemented; provisional thresholds documented. | Not started
CAI-055 | Week 3 | RAG core | Gate policy: ANSWER / PARTIAL / REFUSE | M | CAI-054 | Partial states what was not covered; no parametric gap-fill. | Not started
CAI-056 | Week 3 | RAG core | Refusal registry (full codes) | M | CAI-006 | `NO_RELEVANT_CONTEXT`, `INSUFFICIENT_COVERAGE`, `CONFLICTING_SOURCES`, `OUT_OF_SCOPE`, `ACCESS_DENIED`, `TENANT_SCOPE_EMPTY`, `PROVIDER_UNAVAILABLE` + templates. | Not started
CAI-057 | Week 3 | RAG core | Fail-closed gate behaviour | S | CAI-055 | Any gate error → `REFUSE`; tested. | Not started
CAI-058 | Week 3 | RAG core | Refusal path integration tests | M | CAI-056–057 | Curated unanswerable set returns correct code + message. | Not started
CAI-059 | Week 3 | RAG core | Audit: retrieval funnel + per-claim entailment | M | CAI-043, CAI-051 | Candidate IDs, scores, gate decision reason on every request. | Not started
CAI-060 | Week 3 | RAG core | Draft gold query set (50 queries) | M | CAI-048 | Gov-only, unanswerable, multi-part; labelling guide written. | Not started
CAI-061 | Week 3 | RAG core | Expand gold set to 100+ queries | M | CAI-060 | Domain reviewer pass; double-label overlap sample. | Not started | Domain reviewer availability
CAI-062 | Week 3 | RAG core | Eval script: retrieval metrics | M | CAI-061 | Recall@k, MRR, nDCG offline runner. | Not started
CAI-063 | Week 3 | RAG core | Eval script: generation + citation metrics | M | CAI-061 | Faithfulness, citation precision/recall skeleton. | Not started
CAI-064 | Week 4 | RAG core (required) | Wire eval suite into CI | M | CAI-062–063 | Fails on regression beyond agreed tolerance. | Not started
CAI-065 | Week 4 | RAG core (required) | Calibrate gate thresholds from refusal curve | M | CAI-061, CAI-054 | Replace provisional Phase 6 thresholds with evidence-based values. | Not started
CAI-066 | Week 4 | RAG core (required) | Version-tuple-aware eval result storage | M | CAI-064 | Compare runs only when tuple element under test differs. | Not started
CAI-067 | Week 4 | RAG core (required) | Audit replay: retrieval re-execution | L | CAI-059 | Given `audit_id`, reconstruct tuple + scope; re-run retrieval against pinned snapshot. | Not started
CAI-068 | Week 4 | RAG core (required) | Tier B fallback (optional P1) | L | CAI-065 | Two-pass A then A+B; single retry; `index_key` predicate tests. Skip if Week 3 slipped. | Not started | Optional P1 — skip if Week 3 slips
CAI-069 | Week 4 | RAG core (required) | Tenant doc upload → MinIO → RQ job (optional) | L | CAI-033 | PDF/text only; `farm_id` set; `index_key = tenant_doc`. Skip if time-constrained. | Not started | Optional — skip if time-constrained
CAI-070 | Week 4 | RAG core (required) | Blended retrieval: tenant + gov separate calls | M | CAI-069 | Merge at assembly only; source classes preserved. Depends on CAI-069. | Not started | Blocked on CAI-069 if tenant upload skipped
CAI-071 | Week 4 | RAG core (required) | Cross-farm leak test with real tenant data | M | CAI-069 | Blocking test with two farms; worker vs owner scopes. | Not started | Blocked on CAI-069
CAI-072 | Week 4 | RAG core (required) | E2E demo script + checklist | M | CAI-036, CAI-052 | 5 gov questions, 2 refusals, 1 conflict (if available); audit export sample. | Not started
CAI-073 | Week 4 | RAG core (required) | Operational runbook | S | CAI-072 | Re-embed, snapshot rollback, provider outage, eval rerun commands. | Not started
CAI-074 | Week 4 | RAG core (required) | Diary + PLAN status update | S | CAI-072 | Record metrics, thresholds, known gaps, Phase 11+ triggers fired. | Not started
CAI-075 | Week 4 | Chat ↔ Scheduling integration (Week 4 only — optional / stub) | Read tool: `get_farm_context` | S | CAI-006 | Returns farm metadata + role; re-derives scope from principal. No scheduling logic. | Not started | Optional Week 4 — Scheduling team coordination
CAI-076 | Week 4 | Chat ↔ Scheduling integration (Week 4 only — optional / stub) | Read tool: `list_tasks` / `list_schedules` (read-only) | M | CAI-075 | Calls Scheduling read APIs; structured JSON for orchestrator; audit per tool call. | Not started | Optional — Scheduling read APIs
CAI-077 | Week 4 | Chat ↔ Scheduling integration (Week 4 only — optional / stub) | `POST /api/assistant/schedule-explanations` stub | M | CAI-010 | Accepts schedule snapshot + question; returns explanation draft **without** mutating schedule. Contract aligned with Scheduling team. | Not started | Optional — Scheduling team contract
CAI-078 | Week 4 | Chat ↔ Scheduling integration (Week 4 only — optional / stub) | Proposal tool: `draft_task` (no write) | M | CAI-006 | Creates `draft` record only; owner confirmation required to persist. **No feasibility check in this ticket.** | Not started
CAI-079 | Week 4 | Chat ↔ Scheduling integration (Week 4 only — optional / stub) | Proposal tool: `request_schedule_proposal` (no placement) | M | CAI-077 | Assistant requests Scheduling-generated proposal; assistant explains result; does not influence FarmFlow determinism. | Not started
CAI-080 | Week 4 | Chat ↔ Scheduling integration (Week 4 only — optional / stub) | Orchestration: tools-before-generation | M | CAI-076–079 | Fixed tool set runs before LLM; no model-driven tool loop in POC. | Not started
CAI-081 | Week 4 | Chat ↔ Scheduling integration (Week 4 only — optional / stub) | **Deferred** `evaluate_task_feasibility` read tool | — | CAI-078 | *Description only.* Calls `POST /api/task-feasibility-evaluations` (Scheduling-owned). Returns feasible / better-time / infeasible for **hypothetical** task fields. Chat shows guidance; no schedule write. Phase 11+ unless demo requires it. | Deferred | Deferred to Phase 11+
CAI-082 | Week 4 | Chat ↔ Scheduling integration (Week 4 only — optional / stub) | **Deferred** Chat flow: draft → feasibility → confirm | — | CAI-081 | *Description only.* Owner describes work in chat; assistant drafts task, runs feasibility read, surfaces confirmation UI. Scheduling owns evaluation logic. | Deferred | Deferred to Phase 11+
CAI-083 | Week 4 | Chat ↔ Scheduling integration (Week 4 only — optional / stub) | Joint demo: blended farm doc + gov guidance + schedule explain | M | CAI-070, CAI-077 | Single scripted path for show-and-tell with UI + SCH present. | Not started | Optional joint demo — needs UI + SCH

## Summary
Metric | Value
Total tickets | 83
Done | 20
Done (partial) | 1
Not started | 60
Deferred | 2
Generated (UTC) | 2026-08-28 04:46
Source | docs/CAI_SPRINT_PLAN.md + docs/cai_sprint_tracker.json